## Notes (hidden)
Notes on DP&L's Level 2 Test Documents
- This document contains two parts:
1) The Ohio Level 2 Test Plan--for Dual Billing Option
- Test plan as issued by the state working group
- Parts of the Ohio Test plan not supported by DP&L's test plan:
- Special Meter Read requests not supported
- TP #15 for Net Metering is N/A because DP&L does not have net metering
- Other changes:
- TP #16 uses an 814D to notify of a meter removal. Unless the meter removed represents the last
electric service for a customer, an 814C will be used instead.
2) DP&L's Level 2 Test Script
- Contains the Ohio test conditions arranged in a logical format for efficient testing
- contains all test account numbers, names, etc.
- Additional Notes:
- Testing Dates
- Because of System constraints, DP&L must execute these tests simulating activity around April - June of 2000
- Dates were set to minimize the # of file exchanges required
- Dates Used:
[5 empty] | Date | Initiator | Comment
[5 empty] | 2000-04-17 | Supplier | Initial DASR Requests
[5 empty] | 2000-04-18 | DP&L | Initial DASR Responses + 867 Historical Usage
[5 empty] | 2000-05-15 | DP&L | 814D + 814C
[5 empty] | 2000-05-16 | Supplier | Supplier Response to 5/15; 814D + 814C
[5 empty] | 2000-05-17 | DP&L | DP&L Responses to 5/16 + 814 R+ 814C
[5 empty] | 2000-05-18 | Supplier | Supplier Response to 5/17 + 814R request
[5 empty] | 2000-05-19 | DP&L | DP&L Response to 5/18
[5 empty] | 2000-06-02 | DP&L | 867 Monthly Usage
[5 empty] | 2000-06-05 | Supplier | 824 (for 867)
[5 empty] | 2000-06-05 | DP&L | 867 Cancel and Restatement

## Test Plan EDI - DUAL
Ohio Test Plan for EDI Certification - Enrollment and Billing (Dual)
Supplier
Date Completed
TP #1 High Level Information: |  |  |  | Test Plan #1 - the CRES sends an enrollment request, 814e, in order to enroll a customer; however, the account number on the 814e can not be found in EDU's customer database as a valid account number. Therefore, this enrollment request must be rejected. Meter Type: Single Billing Option: DUAL
Account No: To be provided prior to testing
Test # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results | Filename | Notes
1 | F1 | Supplier | 814e | Enrollment - Create and send enrollment request with an account number that does not exist in EDU's customer database | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back a response rejecting the enrollment due to an invalid account number | REF02 = A76 (Reject Reason Code), REF03 = Account Not Found
TP #2 High Level Information: |  |  |  | Test Plan #2 - the CRES sends an enrollment request, 814e, in order to enroll a customer. The customer has already enrolled with another CRES. The customer cannot be enrolled until the pending enrollment is complete. This enrollment request must be rejected. Meter Type: Single Billing Option: DUAL
Account No: To be provided prior to testing
Test # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
2 | F1 | Supplier | 814e | Enrollment - Create and send enrollment request | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back a response rejecting the enrollment due to not first in | REF02 = NFI (Reject Reason Code), REF03 = Not First In
TP #3 High Level Information: |  |  |  | Test Plan #3 - the CRES sends an enrollment request, 814e, for a customer with secondary request for historical usage information. The EDU replies with an enrollment response, 814er, accepting the enrollment, along with historical usage information, 867hu. Meter Type: Single Kwh/Kw Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing. Test cancel and restate of original billing due to an incorrect read.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
3 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for historical usage. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request and historical usage request | 814er created and sent to CRES
| F2 | Utility | 867 | Hist Usage- EDU send 12 month historical usage information to CRES | 867 created and sent to CRES BPT01=52
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867 created and sent to CRES
| F4 | Utility | 867 | Usage/Monthly- EDU will cancel first month usage | 867 created and sent to CRES
| F5 | Utility | 867 | Usage/Monthly- EDU will restate first month usage | 867 created and sent to CRES
TP #4 High Level Information: |  |  |  | Test Plan #4 - the CRES sends an enrollment request, 814e with secondary request for summary interval meter information and HI detail historical information. The EDU replies with an enrollment response ,814er, accepting the enrollment. Meter Type: Interval Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing of interval meter with summary usage.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
4 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for summary interval meter information. | 814e created and sent to EDU REF02=SUMMARY
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Interval- EDU will send interval usage summarized on a monthly usage transaction | 867
TP #5 High Level Information: |  |  |  | Test Plan #5 - the CRES sends an enrollment request, The EDU replies with an enrollment response ,814er accepting the enrollment. The CRES will request to drop the customer, 814d, then the EDU replies with a drop response, 814dr, accepting the drop. Meter Type: Multiple meters Billing Option: DUAL
Account No: To be provided prior to testing
Biilling: Test an original billing and payment.
Test Acct # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
5 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Supplier | 814d | Drop from Supplier- CRES requests to drop the customer | REF02 = B38 (Dropped by customer request)
| F4 | Utility | 814dr | Drop from Supplier Response- EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
TP #6 High Level Information: |  |  |  | Test Plan #6 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response ,814er accepting the enrollment. Meter Type: Interval Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
6 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for Detail Interval Usage. | 814e created and sent to EDU REF02=DETAIL
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request and secondary request. | 814er created and sent to CRES
| F3 | Supplier | 814c | Change Request- CRES sends change of CRES account number | 814c created and sent by CRES
| F4 | Utility | 814cr | Change Response - EDU response accepting supplier account number change | 814cr created and sent by EDU
| F5 | Utility | 867 | Usage/Detail - EDU will send first month with detail usage | 867 created and sent to CRES
TP #7 High Level Information: |  |  |  | Test Plan #7 - the CRES sends an enrollment request, 814e with a secondary request SR special meter read. The EDU replies with an enrollment response ,814er accepting the enrollment and rejecting the secondary request. Test utility change in customer mailing address. Meter Type: Single Kwh/Kw Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
7 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request with secondary request for SR special meter read. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request and rejecting the secondary request | 814er created and sent to CRES Secondary Request for be Rejected.
| F3 | Utility | 814c | Change request - EDU sends requests to change customer mailing address | 814c created and sent by EDU
| F4 | Supplier | 814cr | Change Response- CRES sends response accepting mailing address change | 814cr created and sent by CRES
| F5 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867mu created and sent to CRES
TP #9 High Level Information: |  |  |  | Test Plan #9 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response, 814er, accepting the enrollment. Meter Type: Multiple meters (Kwh/Kw and Unmetered) Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
9 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly- EDU will send first month usage | 867mu created and sent to CRES
TP #11 High Level Information: |  |  |  | Test Plan #11 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response, 814er, accepting the enrollment. Supplier drops customer after 1 month service. Meter Type: Single Kwh/Kw Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing and final bill.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
11 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly - EDU will send first month usage | 867 created and sent to CRES
| F4 | Supplier | 814d | Drop from Supplier- CRES requests to drop the customer | REF02 = B38 (Dropped by customer request)
| F5 | Utility | 814dr | Drop from Supplier Response- EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
| F6 | Utility | 867 | Usage/Monthly- EDU will send final month usage | 867 created and sent to CRES
TP #12 High Level Information: |  |  |  | Test Plan #12 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response, 814er, accepting the enrollment. Meter Type: Time of Day (On and Off Peak meter) Billing Option: DUAL
Account No: To be provided prior to testing
Billing: Test an original billing.
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
12 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 867 | Usage/Monthly - EDU will send first month usage | 867created and sent to CRES
TP #13 High Level Information: |  |  |  | Test Plan #13 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response ,814er accepting the enrollment. The EDU then requests to drop the customer, 814d, then the CRES replies with a drop response, 814dr, acknowledging the drop. The customer recinds the drop and the EDU sends an 814r to the CRES. The CRES replies with a response acknowledging reinstatement, 814rr. Meter Type: Single Billing Option: DUAL
Account No: To be provided prior to testing
Billing: None
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
13 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment | 814er created and sent to CRES
| F3 | Utility | 814d | Drop from Utility- EDU requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request)
| F4 | Supplier | 814dr | Drop from Utility Response- CRES sends response accepting drop | Ex: ASI = ASI*WQ*024
| F5 | Utility | 814r | Reinstatement- EDU sends requests to reinstate the customer | Ex: ASI = ASI*7*025
| F6 | Supplier | 814rr | Reinstatement Response- CRES sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
TP #14 High Level Information: |  |  |  | Test Plan #14 - the CRES sends an enrollment request, 814e. The EDU replies with an enrollment response ,814er accepting the enrollment. The CRES then requests to drop the customer, 814d, then the EDU replies with a drop response, 814dr, acknowledging the drop. The CRES errored and recinds the drop and the CRES sends an 814r to the EDU. The EDU replies with a response acknowledging reinstatement, 814rr. Meter Type: Single Billing Option: DUAL
Account No: To be provided prior to testing
Billing: None
Test# | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
14 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment | 814er created and sent to CRES
| F3 | Supplier | 814d | Drop from Supplier- Supplier requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request)
| F4 | Utility | 814dr | Drop from CRES Response- EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
| F5 | Supplier | 814r | Reinstatement- CRES sends requests to reinstate the customer | Ex: ASI = ASI*7*025
| F6 | Utility | 814rr | Reinstatement Response- EDU sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
TP #16 High Level Information: |  |  |  | Test Plan #16 - the CRES sends an enrollment request, 814e, The EDU replies with an enrollment response ,814er accepting the enrollment. The EDU removed the second meter and will request meter removal from the account 814c, then the CRES replies with a change response, 814cr, accepting the change. Meter Type: Multiple meters Billing Option: DUAL
Account No: To be provided prior to testing
Biilling: None
Test Acct # | Frame | Responsibility | Transaction | Description of Frame | Expected Results | Actual Results
16 | F1 | Supplier | 814e | Enrollment- Create and send enrollment request. | 814e created and sent to EDU
| F2 | Utility | 814er | Enrollment Response- EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
| F3 | Utility | 814c | Change from EDU for second meter only | REF TD = NM1MR
| F4 | Supplier | 814c | Change from EDU Response- CRES sends response accepting change | Ex: ASI = ASI*WQ*001

## DPL Level II Test Plan (hidden)
DP&L EDI SUPPLIER TESTING SCRIPT | [8 empty] | Prepared By: _________ Date: _________ Executed By: ____________ Date: _____________
TEST PLAN | FRAME | DATE | RESP | ACCOUNT | CUSTOMER NAME | USAGE DETAIL SUMM/DETAIL | BILL OPTION | ACTIVITY | EXPECTED RESULTS | ACTUAL RESULTS | COMMENTS
1 | F1 | 2000-04-17 | S | 5555651450 | Carter, Clarence TP1 | S | DUAL | Enrollment - Create and send enrollment request with an account number that does not exist in EDU's customer database | 814e created and sent to EDU DP&L will reject due to acct number that does not exist
2 | F1 | 2000-04-17 | S | 1282756 | Maples, Marlene TP2 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will reject due to not FIRST IN
3 | F1 | 2000-04-17 | S | 325550826 | Lakeland TP3 Company | S | DUAL | Enrollment - Create and send enrollment request with secondary request for historical usage | 814e created and sent to EDU DP&L will accept and send back 12-months historical usage info on 867hu
4 | F1 | 2000-04-17 | S | 106000 | Mickey TP4 Homes | S | DUAL | Enrollment - Create and send enrollment request with secondary request for summary interval meter information | 814e created and sent to EDU REF02=SUMMARY DP&L will accept enrollment and summarized interval meter info request
5 | F1 | 2000-04-17 | S | 353246923 | Friends Church TP5 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
6 | F1 | 2000-04-17 | S | 418000 | Lassie'e TP6 Treats | D | DUAL | Enrollment - Create and send enrollment request with secondary request for Detail Interval Usage | 814e created and sent to EDU REF02=DETAIL DP&L will accept enrollment and request for detail interval usage
7 | F1 | 2000-04-17 | S | 147597980 | Clinton, James TP7 | S | DUAL | Enrollment - Create and send enrollment request with secondary request for special meter read | 814e created and sent to EDU DP&Lwill accept the enrollment, but reject secondary request for special meter read
8 | F1 | 2000-04-17 | S | 7469662 | Allen, Larry TP8 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
9 | F1 | 2000-04-17 | S | 8505547774 | Barron, Greg TP9 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
10 | F1 | 2000-04-17 | S | 1013726013 | Lewis, Boyd TP10 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
11 | F1 | 2000-04-17 | S | 970690581 | Smith, John TP11 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
12 | F1 | 2000-04-17 | S | 728100 | Spacely TP12 Inc | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L will accept enrollment
13 | F1 | 2000-04-17 | S | 558704 | Jetson, George TP13 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L accepts enrollment
14 | F1 | 2000-04-17 | S | 6246373466 | Jones, Virginia TP14 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L accepts enrollment
16 | F1 | 2000-04-17 | S | 717308491 | Bouquets of Fun TP16 | S | DUAL | Enrollment - Create and send enrollment request | 814e created and sent to EDU DP&L accepts enrollment
1 | F2 | 2000-04-18 | U | 5555651450 | Carter, Clarence TP1 |  |  | Enrollment Response - EDU will send back a response rejecting the enrollment due to an invalid account number | REF02 = A76 (Reject Reason Code) REF03 = Account Not Found
2 | F2 | 2000-04-18 | U | 1282756 | Maples, Marlene TP2 |  |  | Enrollment Response - EDU will send back a response rejecting the enrollment due to not first in | REF02 = NFI (Reject Reason Code) REF03 = Not First In
3 | F2 | 2000-04-18 | U | 325550826 | Lakeland TP3 Company |  |  | Enrollment Response - EDU will send back response accepting the enrollment request and secondary request for historical usage | 814er created and sent to CRES
3 | F2 | 2000-04-18 | U | 325550826 | Lakeland TP3 Company |  |  | Hist Usage - EDU send 12 month historical usage information to CRES | 867 created and sent to CRES BPT01=52
4 | F2 | 2000-04-18 | U | 106000 | Mickey TP4 Homes |  |  | Enrollment Response - EDU will send back response accepting the enrollment request. | 814er created and sent to CRES
5 | F2 | 2000-04-18 | U | 353246923 | Friends Church TP5 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
6 | F2 | 2000-04-18 | U | 418000 | Lassie'e TP6 Treats |  |  | Enrollment Response - EDU will send back response accepting the enrollment request and secondary request | 814er created and sent to CRES
7 | F2 | 2000-04-18 | U | 147597980 | Clinton, James TP7 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request, but rejecting the secondary request for special meter read | 814er created and sent to CRES
8 | F2 | 2000-04-18 | U | 7469662 | Allen, Larry TP8 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
9 | F2 | 2000-04-18 | U | 8505547774 | Barron, Greg TP9 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
10 | F2 | 2000-04-18 | U | 1013726013 | Lewis, Boyd TP10 |  |  | Enrollment Response - EDU will send back response accepting the enrolment request | 814er created and sent to CRES
11 | F2 | 2000-04-18 | U | 970690581 | Smith, John TP11 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
12 | F2 | 2000-04-18 | U | 728100 | Spacely TP12 Inc |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
13 | F2 | 2000-04-18 | U | 558704 | Jetson, George TP13 |  |  | Enrollment Response - EDU will send back response accepting the enrollment | 814er created and sent to CRES
14 | F2 | 2000-04-18 | U | 6246373466 | Jones, Virginia TP14 |  |  | Enrollment Response - EDU will send back response accepting the enrollment | 814er created and sent to CRES
16 | F2 | 2000-04-18 | U | 717308491 | Bouquets of Fun TP16 |  |  | Enrollment Response - EDU will send back response accepting the enrollment request | 814er created and sent to CRES
13 | F3 | 2000-05-15 | U | 558704 | Jetson, George TP13 |  |  | Drop from Utility - EDU requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request) DP&L drops customer fr Choice due to cust request. Effective 6/2/2000
16 | F3 | 2000-05-15 | U | 717308491 | Bouquets of Fun TP16 |  |  | Change from EDU for second meter only | REF TD = NM1MR
5 | F3 | 2000-05-16 | S | 353246923 | Friends Church TP5 |  |  | Drop from Supplier - CRES requests to drop the customer | REF02 = B38 (Dropped by customer request) DP&L will accept DROP and return cust to St Offer. Effective 6/2/2000
8 | F3 | 2000-05-16 | S | 7469662 | Allen, Larry TP8 |  |  | Change Request - CRES sends change of CRES account number | 814c created and sent by CRES DP&L will accept change and MNEL should be updated with new info
11 | F4 | 2000-05-16 | S | 970690581 | Smith, John TP11 |  |  | Drop from Supplier - CRES requests to drop the customer | REF02 = B38 (Dropped by customer request) DP&L will accept drop. Effective 6/2/2000
13 | F4 | 2000-05-16 | S | 558704 | Jetson, George TP13 |  |  | Drop from Utility Response - CRES sends response accepting drop | Ex: ASI = ASI*WQ*024
14 | F3 | 2000-05-16 | S | 6246373466 | Jones, Virginia TP14 |  |  | Drop from Supplier - Supplier requests to drop the customer | Ex: REF02 = B38 (Dropped by customer request) DP&L accepts Drop. Effective 6/2/2000
16 | F4 | 2000-05-16 | S | 717308491 | Bouquets of Fun TP16 |  |  | Change from EDU Response - CRES sends response accepting change | Ex: ASI = ASI*WQ*001
5 | F4 | 2000-05-17 | U | 353246923 | Friends Church TP5 |  |  | Drop from Supplier Response - EDU sends response accepting the drop | Ex: ASI = ASI*WQ*024
7 | F3 | 2000-05-17 | U | 147597980 | Clinton, James TP7 |  |  | Change request - EDU sends requests to change customer mailing address | 814c created and sent by EDU
8 | F4 | 2000-05-17 | U | 7469662 | Allen, Larry TP8 |  |  | Change Response - EDU response accepting supplier account number change | 814cr created and sent by EDU
11 | F5 | 2000-05-17 | U | 970690581 | Smith, John TP11 |  |  | Drop from Supplier Response - EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
13 | F5 | 2000-05-17 | U | 558704 | Jetson, George TP13 |  |  | Reinstatement - EDU sends requests to reinstate the customer | Ex: ASI = ASI*7*025 DP&L sends reinstate cust changed mind. Effective 6/2/2000
14 | F4 | 2000-05-17 | U | 6246373466 | Jones, Virginia TP14 |  |  | Drop from CRES Response - EDU sends response accepting drop | Ex: ASI = ASI*WQ*024
7 | F4 | 2000-05-18 | S | 147597980 | Clinton, James TP7 |  |  | Change Response - CRES sends response accepting mailing address change | 814cr created and sent by CRES
13 | F6 | 2000-05-18 | S | 558704 | Jetson, George TP13 |  |  | Reinstatement Response - CRES sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
14 | F5 | 2000-05-18 | S | 6246373466 | Jones, Virginia TP14 |  |  | Reinstatement - CRES sends requests to reinstate the customer | Ex: ASI = ASI*7*025 DP&L accepts reinstate. Effective 6/2/2000
14 | F6 | 2000-05-19 | U | 6246373466 | Jones, Virginia TP14 |  |  | Reinstatement Response - EDU sends response accepting reinstatement | Ex: ASI = ASI*WQ*025
3 | F3 | 2000-06-02 | U | 325550826 | Lakeland TP3 Company |  |  | Usage/Monthly - EDU will send first month usage | 867 created and sent to CRES DP&L will send first month's usage info on 867mu
4 | F3 | 2000-06-02 | U | 106000 | Mickey TP4 Homes |  |  | Usage/Interval - EDU will send interval usage summarized on a monthly usage transaction | DP&L will send summarized interval meter info
6 | F3 | 2000-06-02 | U | 418000 | Lassie'e TP6 Treats |  |  | Usage/Detail - EDU will send first month with detail usage | 867 created and sent to CRES DP&L will send first months detailed usage
7 | F5 | 2000-06-02 | U | 147597980 | Clinton, James TP7 |  |  | Usage/Monthly - EDU will send first month usage | 867mu created and sent to CRES DP&L will send first month's usage
8 | F5 | 2000-06-02 | U | 7469662 | Allen, Larry TP8 |  |  | Usage/Monthly - EDU will send first month usage | 867mu created ans sent to CRES DP&L will send first months usage
9 | F3 | 2000-06-02 | U | 8505547774 | Barron, Greg TP9 |  |  | Usage/Monthly - EDU will send first month usage | 867mu created and sent to CRES DP&L will send first months usage
10 | F3 | 2000-06-02 | U | 1013726013 | Lewis, Boyd TP10 |  |  | Usage/Monthly - EDU will send first month usage | 867 created and sent to CRES DP&L will send first months usage
11 | F3 | 2000-06-02 | U | 970690581 | Smith, John TP11 |  |  | Usage/Monthly - EDU will send first month usage | 867 created and sent to CRES DP&L will send first months usage
12 | F3 | 2000-06-02 | U | 728100 | Spacely TP12 Inc |  |  | Usage/Monthly - EDU will send first month usage | 867 created and sent to CRES DP&L will send first months on/off peak meter usage
3 | F4 | 2000-06-05 | U | 325550826 | Lakeland TP3 Company |  |  | Usage/Monthly - EDU will cancel first month usage | 867 created and sent to CRES
3 | F5 | 2000-06-05 | U | 325550826 | Lakeland TP3 Company |  |  | Usage/Monthly - EDU will restate first month usage | 867 created and sent to CRES
10 | F4 | 2000-06-05 | S | 1013726013 | Lewis, Boyd TP10 |  |  | Supplier Rejecting 867 | DP&L receives and investigates rejection